## Cover
COVID 19 COST ASSESSMENT TOOLKIT
Tool 1. Data collection template
Professional Practice Task Group
Covid-19 Cost Planning Working Group
Issue 1. July 2020

## Toolkit Inclusions & Exclusions
CLC PRODUCTIVITY MEASURES
APPENDIX A: | Inclusions & Exclusions
Measurable | Inclusions | Exclusions
Revenue | All costs in the monthly cycle: not forecast but actual gross certified value on the project in that month. This includes: | Payments to be excluded are:
| · payments for agreed valued works on-site | · advance payments,
| · payments for agreed valued works off-site | · PCSA payments,
| · materials on and off-site payments | · design payments for Design & Build projects
· all staff payments for the project (all considered on site resources)
· any other payments made
At the end of the project the total sum of all payments should match the agreed final cost
Worked Hours | Hours to be included:
· Project-related staff (whether in a remote office or on-site hours should be calculated as on-site hours)
· Trade / sub-contract management staff which are based on the project
· Operative hours logged on-site through security system
· Preliminaries resources such as Security Staff and Traffic Marshalls (hours worked)
Preliminaries | For actual preliminaries the following to be included | Costs to be excluded are:
| · Additional costs due to prolongation | · Additional Consultants costs
· Subcontractor / Utility Provider additional costs
· Logistics additional costs – signage, gates / barriers, parking, social distancing measures, welfare increase etc
· Materials additional costs – protection of materials on site, alternatives due to non-availability, alternative delivery methods, small quantity surcharge etc
· Site close down / re-establishment costs – CCTV, security, protection, maintenance, removal, deep clean, surveys etc

## Worked Example
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project Alpha Data Entry
| Month of Data Collection: |  |  | 2020-06-01 |  |  | Date to be completed in format 01/06/2020
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High | Highlight required level
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 900000 |  |  | Enter Originally Planned Revenue
| b | Monthly Actual Revenue |  | 500000 |  |  | Enter Actual Revenue
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | 55.56%
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 800 |  |  | Enter total number of workers on site in month
| b | Working Days in Reporting Month |  | 24 |  |  | Enter working days (saturdays = 0.5 day)
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | 33.3333
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 500000
| b | Total Actual Number of Workers on Site from 2a above |  | 800
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | 625
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 500000
| b | Total Actual Man-Hours Worked in Reporting Month |  | 6000 |  |  | Enter number of hours on site if available; if not use full number of working hours per day per worker
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | 83.3333
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 3000000 |  |  | Enter planned total project preliminaries
| b | Actual / Anticipated Total Preliminaries Costs |  | 3500000 |  |  | Enter anticipated total project preliminaries
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | 116.7%
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 September 19
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project 1 Data Entry
| Month of Data Collection: |  |  | 2019-09-01
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 0
| b | Monthly Actual Revenue |  | 0
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | #DIV/0!
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 0
| b | Working Days in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 0
| b | Total Actual Number of Workers on Site from 2a above |  | 0
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | #DIV/0!
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 0
| b | Total Actual Man-Hours Worked in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 0
| b | Actual / Anticipated Total Preliminaries Costs |  | 0
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | #DIV/0!
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 October 2019
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project 1 Data Entry
| Month of Data Collection: |  |  | 2019-10-01
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 0
| b | Monthly Actual Revenue |  | 0
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | #DIV/0!
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 0
| b | Working Days in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 0
| b | Total Actual Number of Workers on Site from 2a above |  | 0
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | #DIV/0!
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 0
| b | Total Actual Man-Hours Worked in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 0
| b | Actual / Anticipated Total Preliminaries Costs |  | 0
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | #DIV/0!
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 November 2019
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project 1 Data Entry
| Month of Data Collection: |  |  | 2019-11-01
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 0
| b | Monthly Actual Revenue |  | 0
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | #DIV/0!
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 0
| b | Working Days in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 0
| b | Total Actual Number of Workers on Site from 2a above |  | 0
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | #DIV/0!
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 0
| b | Total Actual Man-Hours Worked in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 0
| b | Actual / Anticipated Total Preliminaries Costs |  | 0
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | #DIV/0!
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 February 2020
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project 1 Data Entry
| Month of Data Collection: |  |  | 2020-02-01
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 0
| b | Monthly Actual Revenue |  | 0
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | #DIV/0!
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 0
| b | Working Days in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 0
| b | Total Actual Number of Workers on Site from 2a above |  | 0
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | #DIV/0!
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 0
| b | Total Actual Man-Hours Worked in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 0
| b | Actual / Anticipated Total Preliminaries Costs |  | 0
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | #DIV/0!
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 March 2020
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project 1 Data Entry
| Month of Data Collection: |  |  | 2020-03-01
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 0
| b | Monthly Actual Revenue |  | 0
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | #DIV/0!
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 0
| b | Working Days in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 0
| b | Total Actual Number of Workers on Site from 2a above |  | 0
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | #DIV/0!
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 0
| b | Total Actual Man-Hours Worked in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 0
| b | Actual / Anticipated Total Preliminaries Costs |  | 0
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | #DIV/0!
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 April 2020
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project 1 Data Entry
| Month of Data Collection: |  |  | 2020-04-01
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 0
| b | Monthly Actual Revenue |  | 0
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | #DIV/0!
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 0
| b | Working Days in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 0
| b | Total Actual Number of Workers on Site from 2a above |  | 0
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | #DIV/0!
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 0
| b | Total Actual Man-Hours Worked in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 0
| b | Actual / Anticipated Total Preliminaries Costs |  | 0
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | #DIV/0!
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 May 2020
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  |  | Project 1 Data Entry
| Month of Data Collection: |  |  | 2020-05-01
| Project Sector: |  |  | Residential
| Project Region: |  |  | London
| Asset Type: |  |  | Apartment Block
| Level of Offsite Manufacture: |  |  | None / Low | Medium | High
HEADING
1 | PLANNED v ACTUAL REVENUE
| a | Monthly Planned Revenue |  | 0
| b | Monthly Actual Revenue |  | 0
[5 empty] | Indicator to be supplied: Proportion of Planned Revenue recovered as Actual (%) | #DIV/0!
2 | WORKFORCE INDICATOR
| a | Total Actual Number of Workers on Site in Month |  | 0
| b | Working Days in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Average Number of Workers on Site per Day (Nr) | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE
| a | Monthly Actual Revenue from 1a above |  | 0
| b | Total Actual Number of Workers on Site from 2a above |  | 0
[5 empty] | Indicator to be supplied: Revenue Generated per Worker (£) | #DIV/0!
4 | PRODUCTIVITY INDICATOR
| a | Total Actual Revenue from 1b above |  | 0
| b | Total Actual Man-Hours Worked in Reporting Month |  | 0
[5 empty] | Indicator to be supplied: Revenue Generate per Man -Hour (£) | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE)
| a | Planned Total Preliminaries Costs |  | 0
| b | Actual / Anticipated Total Preliminaries Costs |  | 0
[5 empty] | Indicator to be supplied: Actual / Anticipated Total Preliminaries v Planned (%) | #DIV/0!
User input cells
Output cells for CLC tookit metrics on productivity assessment
For inclusions / exclusions in the items above see the CLC toolkit tab

## Project 1 Summary Data
CLC PRODUCTIVITY MEASURES
APPENDIX A: |  | Project 1 Summary Data
| Project Sector: |  | Residential
| Project Region: |  | London
| Asset Type: |  | Apartment Block
| Level of Offsite Manufacture: |  | None / Low | None / Low
| INDICATOR |  | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
1 | PLANNED v ACTUAL REVENUE |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
2 | WORKFORCE INDICATOR |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
3 | OUTPUT INDICATOR OF REVENUE |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
4 | PRODUCTIVITY INDICATOR |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
5 | PRELIMINARIES (TOTAL PROJECT LIFE) |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Data from the relevant tab to May 20 will automatically link
Subsequent periods to be manually added or linked